## Sheet1
Group Member | Date | Time Spent(HH:MM) | Area Worked | Notes
All | 2015-02-23 | 2:00 | Documentation | Prepared for Design Documentation Presentation
All | 2015-02-26 | 0:30 | Documentation | Planning for Design Document
Drew Polhamus | 2015-03-02 | 1:00 | Documentation | Updated Project Plan, still working on it
Drew Polhamus | 2015-03-03 | 2:30 | Documentation | Revised and Updated Project Plan.
Corey Greer | 2015-03-02 | 1:00 | Documentation | Updated Features, Design Overview, Schedule, Ethical Issues, Conclusion, Impact on Society, and Risk and Reliability in the Project Plan
Taylor Ehrhart | 2015-03-03 | 1:30 | Documentation | Added methodologies and deliverables for test plan and individual test documents
Corey Greer | 2015-03-03 | 0:30 | Documentation | Updated Schedule in Project Plan
Taylor, Corey | 2015-03-11 | 1:00 | Planning | Researched RESTful web services to provide caching, data linking and a uniform interface in the entirety of the application
Kevin Dowling | 2015-03-11 | 2:00 | Planning | Researched android studio and android development
Kevin Dowling | 2015-03-14 | 1:30 | Implementation | Started Coding the main menu
Kevin Dowling | 2015-03-15 | :30 | Implementation | Tried to get VT-X to work in my BIOS
Kevin Dowling | 2015-03-16 | 1:00 | Implementation | Got navigation to and from the Main Menu to work
Corey Greer | 2015-03-21 | 2:15 | Research/ Planning | Web service research. 4 HTTP requests & how they will populate activity w/ info.
Kevin Dowling | 2015-03-21 | 2:15 | Debugging/Planning | Connected Corey's phone and loaded the app, Research on UI elements in AS
Corey Greer | 2015-03-27 | :30 | Planning | Found HTTPSService class in Android API
Corey Greer | 2015-03-29 | 1:13 | Planning | Watching videos and reading tutorials on httpService.
Taylor Ehrhart | 2015-03-30 | 3;00 | Research/ Planning | Researched AS API's and packagaes relating to camera feed and grapphics overlay.
Corey Greer | 2015-03-31 | 1:22 | Planning | Found Amazon Web Services, now trying to see if we can use it.
Corey Greer | 2015-04-02 | 1:10 | Planning | Setting up AWS, and learning how to use it.
All | 2015-04-02 | 1:15 | Versioning | Skype group call, setting up BitBucket
Kevin Dowling | 2015-04-02 | 3:30 | Implementation | Worked on the layout of the app. Researched and tried to implement a zoom to the map like looking through a magnifying glass.
Taylor Ehrhart | 2015-04-04 | 2:30 | Planning
Corey Greer | 2015-04-05 | 3:15 | Planning | AWS SimpleDB, Android SDK, Adding libraries to Android Studio, need to update repo
Kevin Dowling | 2015-04-05 | 3:15 | Planning | AWS SimpleDB, Android SDK, Adding libraries to Android Studio, need to update repo
All | 2015-04-06 | :30 | Training | How to update repository
Taylor Ehrhart | 2015-04-09 | 2:00 | Research/ Planning | Restarted work on launching camera - researched intents and their uses
Kevin Dowling | 2015-04-09 | 3:00 | Implementation | Facility List/ Facility Page. Removing action bar.
Kevin Dowling | 2015-04-12 | 3:00 | Design | Working on communication between web service and database. Looked at where http requests are going to go in the code with Corey
Corey Greer | 2015-04-12 | 3:00 | Design | Working on communication between web service and database. Looked at where http requests are going to go in the code with Kevin.
All | 2015-04-14 | 1:50 | Design | Working on setting up a VPC through AWS; ran into issues with the CIDR block specifiying regional access limits - cannot connect the VPC to SQL db
Kevin Dowling | 2015-04-17 | 3:00 | Implementation | Got the camera to give a feed
Corey Greer | 2015-04-18 | 4:00 | Research/ Planning | Updated design doc, aws might be too complex. Looking at mysql, java dataSource
Corey Greer, All | 2015-04-20 | 3:40 | Research/ Planning | Hosted meeting in Library explaining http requests, looked at database & created a table in a project on my machine. Can't tell if this is in our cloud database.
Drew Polhamus | 2015-04-21 | 1:00 | Research/ Planning | Learned how to use MS SQL Server and how to manipulate and manage databases
Corey Greer | 2015-04-23 | 1:45 | Research/ Planning | Isolated my database connection problem to either the database not accepting remote access, or my firewall settings. Since Drew is able to connect remotely, I'm thinking it might be firewall in my machine.
Corey Greer | 2015-04-24 | 1:30 | Implementation | I think I have connected to the database. I didn't change any settings, just tried again, and I didn't get the normal error message.
Taylor Ehrhart | 4/24/0205 | 2:00 | Documentation | Created a requirements traceability matrix in Excel to manage status and testing of individual functional requirements.
All | 2015-04-25 | 1:15 | Implementation | Met to start populating cells in the database.
Taylor Ehrhart | 2015-04-26 | 2:00 | Documentation | I started devising positive and negative test cases for each functional requirment.
Corey, Kevin, Taylor | 2015-04-29 | 3:00 | Documentation | Final touches to all documents improving readability, format, etc. Test plans were added, database section was updated, some formatting was modified and technical runovers were performed.